## Project Planner
Project Planner
|  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
Frameworks to Support Continuous Delivery | [9 empty] | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [5 empty] | % Complete (beyond plan)
FEATURE | REQUIREMENT | DESCRIPTION | AGENT | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
 | time axis 2017-09-13 to 2018-04-06
N/A | N/A | Project searching | Team | 2017-09-13 | 14 | 2017-09-13 | 22 | 100%
N/A | N/A | Initial meeting with professor for requirements | Team | 2017-10-05 | 7 | 2017-10-19 | 1 | 100%
N/A | N/A | Assign roles for team | Team | 2017-10-19 | 1 | 2017-10-19 | 1 | 100%
N/A | N/A | Create project description and context diagram | Gurpreet | 2017-10-20 | 2 | 2017-10-21 | 2 | 100%
N/A | N/A | Write system requirements | Team | 2017-10-20 | 2 | 2017-10-21 | 2 | 100%
N/A | N/A | Create project planner with planned and actually completed work | Paul | 2017-10-20 | 2 | 2017-10-21 | 2 | 100%
Feature 1 | FR 1 | Extract commits from a .git directory | Gurpreet | 2017-10-25 | 2 | 2017-11-08 | 2 | 100%
Feature 1 | FR 2 | Analyze and record classes/methods effected by each commit | Paul | 2017-10-27 | 5 | 2017-11-14 | 5 | 100%
Feature 1 | FR 3 | Process and record the amount of code changed with each commit | Gurpreet | 2017-11-01 | 4 | 2017-11-28 | 4 | 100%
Feature 2 | FR 1 | Record results of the test suite each time it is run | Paul | 2017-11-05 | 2 |  |  | 0%
Feature 2 | FR 2 | During test phase inject previous risk analysis | Gurpreet | 2017-11-07 | 3 |  |  | 0%
Feature 3 | FR 1 | Record issues filed for the code base | Gurpreet | 2017-11-10 | 3 |  |  | 0%
Feature 3 | FR 2 | Connect issues to their resolution and make an inference from the association | Paul | 2017-11-13 | 6 |  |  | 0%
Feature 4 | QR 1 | Allow parsing from diverse options (User newsgroups, technical reports, etc) | Gurpreet | 2017-11-19 | 5 |  |  | 0%
Feature 5 | FR 1 | Standardize and combine Git data into a central data model | Paul | 2017-11-24 | 4 |  |  | 0%
Feature 5 | FR 2 | Standardize and combine test data into a central data model | Paul | 2017-11-28 | 3 |  |  | 0%
Feature 5 | FR 3 | Standardize and combine issue data into a central data model | Gurpreet | 2017-12-01 | 3 |  |  | 0%
Feature 6 | FR 1 | In the data model figure out risky parts of the code and mark them | Paul | 2018-01-03 | 4 |  |  | 0%
Feature 6 | FR 2 | Identify issue keywords that are higher risk than others | Paul | 2018-01-07 | 7 |  |  | 0%
Feature 6 | FR 3 | Identify impact when a test is changed (how much coverage it offers) | Gurpreet | 2018-01-14 | 7 |  |  | 0%
Feature 7 | FR 1 | Create a PDF report for stakeholders to see progress in codebase | Gurpreet | 2018-01-21 | 3 |  |  | 0%
Feature 7 | FR 2 | Create a Web view for exploring the risk of the codebase | Paul | 2018-01-24 | 3 |  |  | 0%
Feature 7 | FR 3 | Create Github, IFTTT and Slack integrations for viewing framework data model | Gurpreet | 2018-01-27 | 5 |  |  | 0%
Feature 8 | FR 1 | Create test integration so developer can see risk rating when conducting tests | Paul | 2018-02-15 | 5 |  |  | 0%
Feature 8 | FR 2 | Develop command line interface to the framework | Gurpreet | 2018-02-20 | 7 |  |  | 0%
Feature 8 | FR 3 | Research deployment frameworks and integrate risk analysis into pipe line | Paul | 2018-02-27 | 7 |  |  | 0%
Feature 9 | FR 1 | Develop VIM plugin for viewing risk rating of each method/class | Gurpreet | 2018-03-06 | 6 |  |  | 0%
Feature 9 | FR 2 | Develop IDEA plugin for viewing risk rating of each method/class | Paul | 2018-03-12 | 5 |  |  | 0%
Feature 10 | FR 1 | Make the framework easily deployable into a microservice | Paul | 2018-03-17 | 8 |  |  | 0%
Feature 10 | FR 2 | Reduce dependencies and deliver a minimally intrusive product | Gurpreet | 2018-03-25 | 8 |  |  | 0%
Formulas:
Milestone 1 = [Milestone 2, row above]+[Milestone 1, row above]