## Project Planner
Project Planner
|  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4
Frameworks to Support Continuous Delivery | [9 empty] | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (before plan) | [5 empty] | % Complete (beyond plan)
FEATURE | REQUIREMENT | DESCRIPTION | AGENT | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
 | time axis 2017-09-13 to 2018-04-06
N/A | N/A | Project searching | Team | 2017-09-13 | 14 | 2017-09-13 | 22 | 100%
N/A | N/A | Initial meeting with professor for requirements | Team | 2017-10-05 | 7 | 2017-10-19 | 1 | 100%
N/A | N/A | Assign roles for team | Team | 2017-10-19 | 1 | 2017-10-19 | 1 | 100%
N/A | N/A | Create project description and context diagram | Gurpreet | 2017-10-20 | 2 | 2017-10-21 | 2 | 100%
N/A | N/A | Write system requirements | Paul | 2017-10-20 | 2 | 2017-10-21 | 2 | 100%
N/A | N/A | Create project planner with planned and actually completed work | Paul | 2017-10-20 | 2 | 2017-10-21 | 2 | 100%
Feature 1 | FR 1 | Pass code through cdif2rsf to generate rsf | Gurpreet | 2018-02-20 | 2 |  |  | 0%
Feature 1 | FR 2 | Clean up incorrect entity and relationships | Paul | 2018-02-22 | 2 |  |  | 0%
Feature 1 | FR 3 | Store in accessible data storage for next step to use | Gurpreet | 2018-02-24 | 1 |  |  | 0%
Feature 2 | FR 1 | Compare each token to codebase to find valid functions | Paul | 2018-02-25 | 1 | 2018-02-18 | 2 | 100%
Feature 2 | FR 2 | Expand initial token set by a factor of 3 | Gurpreet | 2018-02-26 | 2 | 2018-02-20 | 3 | 100%
Feature 2 | FR 3 | Use NLP to determine question context | Gurpreet | 2018-02-28 | 1 |  |  | 0%
Feature 3 | FR 1 | Run LSI on each token and generate search space for each | Paul | 2018-03-01 | 1 | 2018-02-20 | 3 | 100%
Feature 3 | FR 2 | Expand the search space for each result in FR 1 | Gurpreet | 2018-03-02 | 1 | 2018-02-23 | 3 | 100%
Feature 3 | FR 3 | Find similarities between the initial token expansion and the final set of tokens | Paul | 2018-03-03 | 2 | 2018-02-23 | 3 | 100%
Feature 3 | FR 4 | Apply ranking equation from research paper to come up with final outcome | Paul | 2018-03-05 | 2 | 2018-02-26 | 3 | 100%
Feature 4 | FR 1 | Scan user’s Github repos using Github’s API | Gurpreet | 2018-03-07 | 1 |  |  | 0%
Feature 4 | FR 2 | Allow the user to select ones they wish to run processing on | Paul | 2018-03-08 | 1 |  |  | 0%
Feature 4 | FR 3 | Remember which ones the user selected by storing on backend | Paul | 2018-03-09 | 1 |  |  | 0%
Feature 5 | FR 1 | Monitor output from backend endpoints showing new results for user’s repos | Gurpreet | 2018-03-10 | 1 |  |  | 0%
Feature 5 | FR 2 | When a new bug report is created, and the processing finishes, show the output of that processing on a separate page | Paul | 2018-03-11 | 2 |  |  | 0%
Feature 5 | FR 3 | Allow the user to rerun processing on a specific bug report by sending a request to backend | Gurpreet | 2018-03-13 | 2 |  |  | 0%
Feature 6 | FR 1 | On first usage redirect user to Github’s App authentication page | Gurpreet | 2018-03-15 | 2 |  |  | 0%
Feature 6 | FR 2 | Ask backend to associate bug reports and repositories with this user | Paul | 2018-03-17 | 3 |  |  | 0%
Feature 6 | FR 3 | Redirect user to main UI | Gurpreet | 2018-03-20 | 1 |  |  | 0%
Feature 7 | FR 1 | Allow registration using Github Auth | Paul | 2018-03-21 | 1 | 2018-03-02 | 4 | 100%
Feature 7 | FR 2 | Allow retrieval of processing results for each bug report | Gurpreet | 2018-03-22 | 2 | 2018-03-04 | 2 | 100%
Feature 7 | FR 3 | Continuously improve and modify RSF and keywords as code/bugs change | Paul | 2018-03-24 | 2 |  |  | 0%
Feature 7 | FR 4 | Create an API where the UI can fetch everything from | Gurpreet | 2018-03-26 | 2 | 2018-03-08 | 2 | 100%
Feature 8 | FR 1 | Automate RSF generation when a new repository is linked | Gurpreet | 2018-03-26 | 2 |  |  | 0%
Feature 8 | FR 2 | Automate keyword generation when a new repository is linked | Paul | 2018-03-28 | 1 |  |  | 0%
Feature 8 | FR 3 | Continuously improve and modify RSF and keywords as code/bugs change | Paul | 2018-03-29 | 2 |  |  | 0%
Feature 9 | FR 1 | Monitor marked repositories for each registered user and trigger when new issue is filed | Gurpreet | 2018-03-31 | 2 | 2018-03-13 | 2 | 100%
Feature 9 | FR 2 | Run through automated ranking algorithm | Gurpreet | 2018-04-02 | 1 |  |  | 0%
Feature 9 | FR 3 | Store result for later retrieval | Gurpreet | 2018-04-03 | 1 |  |  | 0%
Feature 9 | FR 4 | Be able to connect to a repository and fetch an issue when it is posted | Gurpreet | 2018-04-04 | 1 | 2018-03-14 | 1 | 100%
Feature 10 | FR 1 | Combine entity generation into token generation | Gurpreet | 2018-04-04 | 2 |  |  | 0%
Feature 10 | FR 2 | Combine FR1 with RSF processing all into one unit | Gurpreet | 2018-04-06 | 1 |  |  | 0%
Feature 10 | FR 3 | Move all functionality to an exposed part of the API | Gurpreet | 2018-04-07 | 1 |  |  | 0%
Feature 10 | FR 4 | Create all endpoints for data processing functionality | Gurpreet | 2018-04-08 | 2 | 2018-03-18 | 3 | 100%
Formulas:
Milestone 1 = [Milestone 2, row above]+[Milestone 1, row above]